## Summary
SAMPLE REPORT. Sample report. Contains no export-controlled (ITAR/EAR) data.
IA9100 Transition Gap Analysis
Measured against the IA9100 changes the IAQG has published to date (draft); the final text may still change them.
Prepared for Meridian Aerostructures. Contains proprietary methodology of Aegis Technologies Inc.; licensed for the recipient's internal use only. Not to be reproduced, shared outside the recipient's organization, used to train or prompt AI systems, or used to develop competing products.
Prepared for | Meridian Aerostructures
Site | -
Report date | 2026-10-22
Records read on | 2026-10-03
Transition readiness | Significant work needed before transition
What it means | Your records show gaps against many of the published IA9100 changes. Plan the work to close them well ahead of your transition audit.
Steps in your action plan | 27
Transition questions answered | 30 of 30
Status | Changes | What it means
Gap | 13 | Your records show it is not in place.
Partly evidenced | 14 | Your records show part of it, or show it with exceptions to close.
Evidenced | 4 | Your records show the requirement in place.
Not assessable from the records supplied | 0 | Nothing supplied shows it either way; the action says what would.
Changes measured | 31
Change area | Changes | Gap | Partly evidenced | Evidenced | Not assessable from the records supplied | First step
Product safety | 7 | 3 | 4 | 0 | 0 | 1
Information security and data protection | 3 | 2 | 0 | 1 | 0 | 7
Organizational culture and ethics | 6 | 2 | 2 | 2 | 0 | 8
Product quality planning and foreign object prevention | 5 | 0 | 4 | 1 | 0 | 16
Counterfeit parts prevention | 7 | 4 | 3 | 0 | 0 | 2
Sub-tier supplier control | 2 | 1 | 1 | 0 | 0 | 4
Production process verification | 1 | 1 | 0 | 0 | 0 | 11

## Action plan
SAMPLE REPORT. Sample report. Contains no export-controlled (ITAR/EAR) data.
Measured against the IA9100 changes the IAQG has published to date (draft); the final text may still change them.
Work through the steps in order. Fill in the owner, the target date and Done (Yes or No) as you go.
Step | Phase | Change area | Clause | Requirement | Status | What to do | Evidence that closes it | Your records | Owner | Target date | Done
1 | 1. Close the gaps | Product safety | 8.1.3 b | Safety risks from identified hazards are analyzed, assessed and controlled | Gap | Assess each safety risk found and record the control applied to it, linking safety-related failure modes to the controls in your control plans. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 15 more. | Each of the 21 records under Your records shows the action done; IA-8.1.3-02 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-8.1.1-004 brought to Conforming. | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106
2 | 1. Close the gaps | Counterfeit parts prevention | 8.1.4 a | People in procurement, receiving inspection, shipping inspection and material control are trained to recognize and prevent counterfeit parts | Gap | Train everyone in procurement, receiving inspection, shipping inspection and material control in counterfeit-part awareness and prevention, and record it in the training matrix. Start with MER-E008, MER-E014, MER-E019, MER-E023, MER-E028, MER-E037 and 5 more. | Each of the 11 records under Your records shows the action done; your AS9100D self-assessment answer QB-8.1.4-002 brought to Conforming. | MER-E008, MER-E014, MER-E019, MER-E023, MER-E028, MER-E037, MER-E038, MER-E043, MER-E046, MER-E065, MER-E067
3 | 1. Close the gaps | Counterfeit parts prevention | 8.1.4 c | Parts are bought from original or authorized manufacturers, authorized distributors or other approved sources | Gap | Buy only from original manufacturers, their authorized distributors or sources you have approved, and record the source's authorization on the supplier list. Start with CF-MER-001, CF-MER-002, SUP-MER-01, SUP-MER-02, SUP-MER-03, SUP-MER-12 and 1 more. | Each of the 7 records under Your records shows the action done; your AS9100D self-assessment answers QB-8.1.4-001 and QB-8.1.4-002 brought to Conforming. | CF-MER-001, CF-MER-002, SUP-MER-01, SUP-MER-02, SUP-MER-03, SUP-MER-12, SUP-MER-17
4 | 1. Close the gaps | Sub-tier supplier control | 8.4.3 k.d | The level of control of direct and sub-tier external providers is determined and communicated | Gap | Decide the level of control for each direct supplier and its sub-tier suppliers, and state it in the information you send them. Start with FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16 and 1 more. | Each of the 7 records under Your records shows the action done; IA-8.4.3-02 answered Conforming in template 30, naming the record that shows it as the evidence seen. | FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17
5 | 1. Close the gaps | Product safety | 8.1.3 c | Changes that could affect product safety are identified and managed | Gap | Record, for every product or process change, whether it can affect product safety and what was done about it, before the change is approved. Start with ECR-MER-040, ECR-MER-043, ECR-MER-044, ECR-MER-045. | Each of the 4 records under Your records shows the action done; IA-8.1.3-03 answered Conforming in template 30, naming the record that shows it as the evidence seen. | ECR-MER-040, ECR-MER-043, ECR-MER-044, ECR-MER-045
6 | 1. Close the gaps | Product safety | 8.1.3 d | The effectiveness of the product-safety processes is assessed | Gap | Review the product-safety processes at set intervals (for example at management review) and record whether they are working. | IA-8.1.3-04 answered Conforming in template 30, naming the record that shows it as the evidence seen.
7 | 1. Close the gaps | Information security and data protection | 7.1.7 | Information security is planned, put in place and controlled to protect the quality management system | Gap | Issue a controlled information security plan or policy covering the systems and data the quality management system depends on, with its controls, incident response and remote access. | IA-7.1.7-02 and IA-7.1.7-03 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-4.1-007 brought to Conforming.
8 | 1. Close the gaps | Organizational culture and ethics | 5.1.1 l | Top management promotes an ethical work environment: conduct policy, training, reporting channels, investigation and resolution, and no penalty for raising a concern | Gap | Issue a code of conduct, train people on it periodically, provide a confidential channel for concerns (product-safety concerns included), and record how each concern was investigated and resolved without penalty to the person who raised it. | IA-5.1.1-03, IA-5.1.1-04 and IA-5.1.1-05 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-5.1-005 brought to Conforming.
9 | 1. Close the gaps | Counterfeit parts prevention | 8.1.4 b | A parts obsolescence monitoring program is applied | Gap | Set up parts obsolescence monitoring for the parts you buy, so that end-of-life parts are found before you are pushed to unapproved sources. | IA-8.1.4-02 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-8.1.4-003 brought to Conforming.
10 | 1. Close the gaps | Counterfeit parts prevention | 8.1.4 e | Verification and test methods are used to detect counterfeit parts | Gap | Define the receiving checks and tests used to detect counterfeit parts, by part risk, and record them on each receipt. | Your AS9100D self-assessment answer QB-8.1.4-002 brought to Conforming.
11 | 1. Close the gaps | Production process verification | 8.5.1.3 | Production process verification goes beyond first article inspection, covering new or changed processes | Gap | Verify every new or changed production process (not only the first part) before production, and record the result with the first article report. Start with FAI-MER-101, FAI-MER-102, FAI-MER-103, FAI-MER-106, FAI-MER-107, FAI-MER-108 and 12 more. | Each of the 18 records under Your records shows the action done; IA-8.5.1.3-01 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-AS9102-001 brought to Conforming. | FAI-MER-101, FAI-MER-102, FAI-MER-103, FAI-MER-106, FAI-MER-107, FAI-MER-108, FAI-MER-110, FAI-MER-111, FAI-MER-112, FAI-MER-113, FAI-MER-114, FAI-MER-115, FAI-MER-116, FAI-MER-117, FAI-MER-118, FAI-MER-104, FAI-MER-105, FAI-MER-109
12 | 1. Close the gaps | Information security and data protection | 7.5.3.1 | Electronic documented information is protected: against loss, by access control, off-site copies, and against unauthorized or unintended change and corruption | Gap | Define and keep the protections for electronic records: who can access and change them, how changes are traced, and off-site backups whose restore has been tested. | IA-7.5.3.1-02 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-7.5-002 brought to Conforming.
13 | 1. Close the gaps | Organizational culture and ethics | 7.3 | People are aware of the importance of ethical behavior | Gap | Record ethics awareness training for everyone, and repeat it at a set interval. | IA-5.1.1-03 answered Conforming in template 30, naming the record that shows it as the evidence seen.
14 | 2. Complete what is partly in place | Product safety | 8.1.3 a | Hazards to product safety are identified, both from events that have happened and by looking ahead | Partly evidenced | Record how hazards to product safety are found: from events and escapes after the fact, and from forward-looking analysis such as hazard analysis or PFMEA. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 15 more. | Each of the 21 records under Your records shows the action done; IA-8.1.3-01 answered Conforming in template 30, naming the record that shows it as the evidence seen. | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106
15 | 2. Complete what is partly in place | Counterfeit parts prevention | 8.1.4 d | Parts and components can be traced to their original or authorized manufacturer | Partly evidenced | Hold a conforming certificate that traces each lot to its original or authorized manufacturer before the lot is released. Start with TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15, TRC-MER-19 and 5 more. | Each of the 11 records under Your records shows the action done. | TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15, TRC-MER-19, TRC-MER-22, TRC-MER-25, TRC-MER-35, TRC-MER-36, TRC-MER-38
16 | 2. Complete what is partly in place | Product quality planning and foreign object prevention | 7.1.5.1 NOTE | Measurement variation is understood through measurement systems analysis, gauge R&R or attribute studies | Partly evidenced | Run and record measurement systems analysis for the gauges that measure key characteristics, and act on studies that are not acceptable. Start with SPC-3107-HARD, SPC-3101-BORE, SPC-3101-FLANGE, GRR-HT2205, GRR-BG6601, GRR-CMM4401. | Each of the 6 records under Your records shows the action done. | SPC-3107-HARD, SPC-3101-BORE, SPC-3101-FLANGE, GRR-HT2205, GRR-BG6601, GRR-CMM4401
17 | 2. Complete what is partly in place | Product safety | 8.1.3 g | Safety events are reported to customers, authorities and type certificate holders as their requirements say | Partly evidenced | Keep a record of each safety event and of its report to the customer, authority or type certificate holder, within the time their requirements set. Start with BOEING-QN-2291, BOEING-SCAR-D1-4426-003, GE-QN-0448, SPIRIT-CAR-7712. | Each of the 4 records under Your records shows the action done. | BOEING-QN-2291, BOEING-SCAR-D1-4426-003, GE-QN-0448, SPIRIT-CAR-7712
18 | 2. Complete what is partly in place | Counterfeit parts prevention | 8.1.4 g | Suspect or detected counterfeit parts are segregated, contained and reported | Partly evidenced | Quarantine every suspect part, contain where it went, and report each confirmed or suspect case externally (for example to GIDEP and the customer). Start with CF-MER-001, CF-MER-002, CF-MER-003. | Each of the 3 records under Your records shows the action done. | CF-MER-001, CF-MER-002, CF-MER-003
19 | 2. Complete what is partly in place | Product safety | 8.1.3 e | People with product-safety responsibilities are trained in them | Partly evidenced | Add product-safety responsibilities training to the training matrix for the roles that hold them, and keep it current. | IA-8.1.3-05 answered Conforming in template 30, naming the record that shows it as the evidence seen.
20 | 2. Complete what is partly in place | Product safety | 8.1.3 f | Product-safety information, safety events and changes to safety procedures are communicated to the people who need them | Partly evidenced | Set out how safety-critical information, safety events and changes to safety procedures reach the people concerned, and keep a record that they did. | IA-8.1.3-06 answered Conforming in template 30, naming the record that shows it as the evidence seen.
21 | 2. Complete what is partly in place | Organizational culture and ethics | 0.1, 0.2 | The introduction now treats organizational culture and ethical behavior as part of an effective quality management system | Partly evidenced | State in the quality manual how culture and ethical behavior support the quality management system, and point to the policy and objectives that carry it. | Your AS9100D self-assessment answer QB-5.1-005 brought to Conforming.
22 | 2. Complete what is partly in place | Counterfeit parts prevention | 8.1.4 f | Counterfeit-part reports from external sources (for example GIDEP) are monitored | Partly evidenced | Assign someone to review external counterfeit-part reports (for example GIDEP alerts) at a set interval and record what was checked against your parts. | IA-8.1.4-05 answered Conforming in template 30, naming the record that shows it as the evidence seen.
23 | 2. Complete what is partly in place | Product quality planning and foreign object prevention | 8.1 b NOTE | Statistical techniques support process control: key characteristics, capability, control plans, statistical process control | Partly evidenced | Keep control plans and capability studies for key characteristics current, and act on processes whose capability is low. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 25 more. | Each of the 31 records under Your records shows the action done. | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106, SPC-3107-HARD, CP-MER-3101, CP-MER-3103, CP-MER-3104, CP-MER-3105, CP-MER-3106, SPC-3101-BORE, SPC-3104-BORE, SPC-3101-FLANGE, SPC-3108-HINGE
24 | 2. Complete what is partly in place | Product quality planning and foreign object prevention | 8.1 NOTE | Product and service provision is planned as integrated, phased processes (project or program management, APQP) | Partly evidenced | Plan each new product or program in phases with gate reviews (APQP or equivalent), and close each phase's outputs (PFMEA, control plan, PPAP) before the next. Start with PPAP-MER-3101, PPAP-MER-3102, PPAP-MER-3103, PPAP-MER-3104, PPAP-MER-3105, PPAP-MER-3106 and 21 more. | Each of the 27 records under Your records shows the action done; IA-8.1-03 answered Conforming in template 30, naming the record that shows it as the evidence seen; your AS9100D self-assessment answer QB-8.1.1-003 brought to Conforming. | PPAP-MER-3101, PPAP-MER-3102, PPAP-MER-3103, PPAP-MER-3104, PPAP-MER-3105, PPAP-MER-3106, FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106
25 | 2. Complete what is partly in place | Product quality planning and foreign object prevention | 8.1 k | Operations are planned to prevent, detect and mitigate foreign objects and debris | Partly evidenced | Make foreign object and debris a planned control: name it in PFMEAs and control plans where it can occur, keep the FOD procedure current and train the people in FOD areas. Start with PFMEA-MER-3101, PFMEA-MER-3102, PFMEA-MER-3103, PFMEA-MER-3104, NCR-MER-213, CAPA-MER-013 and 2 more. | Each of the 8 records under Your records shows the action done; your AS9100D self-assessment answers QB-8.5.1-011 and QB-5.1-004 brought to Conforming. | PFMEA-MER-3101, PFMEA-MER-3102, PFMEA-MER-3103, PFMEA-MER-3104, NCR-MER-213, CAPA-MER-013, MER-E020, DOC-MER-039
26 | 2. Complete what is partly in place | Sub-tier supplier control | 8.4.1 | External providers are required to apply suitable controls to their own direct and sub-tier providers | Partly evidenced | Require each supplier, in the purchase order or supplier quality manual, to control its own suppliers to your requirements, and record that requirement in the flow-down register. Start with FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16 and 9 more. | Each of the 15 records under Your records shows the action done. | FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17, FLD-MER-02, FLD-MER-03, FLD-MER-04, FLD-MER-05, FLD-MER-12, FLD-MER-09, FLD-MER-10, FLD-MER-18
27 | 2. Complete what is partly in place | Organizational culture and ethics | 8.4.3 | External providers are told of the importance of ethical behavior | Partly evidenced | Add the importance of ethical behavior to your purchase order terms or supplier quality manual, and record it in the flow-down register. | IA-8.4.3-01 answered Conforming in template 30, naming the record that shows it as the evidence seen.

## Requirements
SAMPLE REPORT. Sample report. Contains no export-controlled (ITAR/EAR) data.
Measured against the IA9100 changes the IAQG has published to date (draft); the final text may still change them.
# | Clause | Requirement | Topic | Change | Status | What your records show | Your records | Action | Rank
1 | 8.1.3 a | Hazards to product safety are identified, both from events that have happened and by looking ahead | Product safety | Was guidance; now a requirement | Partly evidenced | IA-8.1.3-01: Observation (Hazards found from events only; no forward-looking hazard analysis). Open findings in your records: High-priority failure mode with no control (FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02 and 16 more). | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106 | Record how hazards to product safety are found: from events and escapes after the fact, and from forward-looking analysis such as hazard analysis or PFMEA. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 15 more. | 14
2 | 8.1.3 b | Safety risks from identified hazards are analyzed, assessed and controlled | Product safety | Was guidance; now a requirement | Gap | IA-8.1.3-02: Nonconforming (No safety risk assessment or recorded controls). Your AS9100D self-assessment answer QB-8.1.1-004 is Nonconforming (See audit programme for 8.1.1): the base this change builds on is not in place. Open findings in your records: High-priority failure mode with no control (FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02 and 16 more). | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106 | Assess each safety risk found and record the control applied to it, linking safety-related failure modes to the controls in your control plans. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 15 more. | 1
3 | 8.1.3 c | Changes that could affect product safety are identified and managed | Product safety | Was guidance; now a requirement | Gap | IA-8.1.3-03: Nonconforming (Change form has no product-safety question). 4 of 5 open product or process changes carry no risk assessment yet, so their effect on product safety is not recorded (ECR-MER-040, ECR-MER-043, ECR-MER-044, ECR-MER-045). | ECR-MER-040, ECR-MER-043, ECR-MER-044, ECR-MER-045 | Record, for every product or process change, whether it can affect product safety and what was done about it, before the change is approved. Start with ECR-MER-040, ECR-MER-043, ECR-MER-044, ECR-MER-045. | 5
4 | 8.1.3 d | The effectiveness of the product-safety processes is assessed | Product safety | Was guidance; now a requirement | Gap | IA-8.1.3-04: Nonconforming (No review of the safety processes on record). |  | Review the product-safety processes at set intervals (for example at management review) and record whether they are working. | 6
5 | 8.1.3 e | People with product-safety responsibilities are trained in them | Product safety | Was guidance; now a requirement | Partly evidenced | IA-8.1.3-05: Observation (Product safety awareness in induction only; no role training). |  | Add product-safety responsibilities training to the training matrix for the roles that hold them, and keep it current. | 19
6 | 8.1.3 f | Product-safety information, safety events and changes to safety procedures are communicated to the people who need them | Product safety | Was guidance; now a requirement | Partly evidenced | IA-8.1.3-06: Observation (Safety events shared verbally; not recorded). |  | Set out how safety-critical information, safety events and changes to safety procedures reach the people concerned, and keep a record that they did. | 20
7 | 8.1.3 g | Safety events are reported to customers, authorities and type certificate holders as their requirements say | Product safety | Was guidance; now a requirement | Partly evidenced | Open findings in your records: Customer escape caused by a supplier (BOEING-QN-2291, BOEING-SCAR-D1-4426-003, GE-QN-0448, SPIRIT-CAR-7712). IA-8.1.3-07: Conforming (Customer notification procedure QP-8.7-02). | BOEING-QN-2291, BOEING-SCAR-D1-4426-003, GE-QN-0448, SPIRIT-CAR-7712 | Keep a record of each safety event and of its report to the customer, authority or type certificate holder, within the time their requirements set. Start with BOEING-QN-2291, BOEING-SCAR-D1-4426-003, GE-QN-0448, SPIRIT-CAR-7712. | 17
8 | 7.1.7 | Information security is planned, put in place and controlled to protect the quality management system | Information security and data protection | New in IA9100 | Gap | IA-7.1.7-03: Nonconforming (Shared login for the CMM vendor's remote support). IA-7.1.7-02: Observation (Incidents handled by the IT contractor; no record of who is told). Your AS9100D self-assessment answer QB-4.1-007 is an Observation (See audit programme for 4.1). IA-7.1.7-01: Conforming (Information security policy ISP-01 rev 2). |  | Issue a controlled information security plan or policy covering the systems and data the quality management system depends on, with its controls, incident response and remote access. | 7
9 | 7.5.3.1 | Electronic documented information is protected: against loss, by access control, off-site copies, and against unauthorized or unintended change and corruption | Information security and data protection | Strengthened | Gap | IA-7.5.3.1-02: Nonconforming (Restore never tested). Your AS9100D self-assessment answer QB-7.5-002 is an Observation (See audit programme for 7.5). IA-7.5.3.1-01: Conforming (ERP role matrix ERP-RM-04). |  | Define and keep the protections for electronic records: who can access and change them, how changes are traced, and off-site backups whose restore has been tested. | 12
10 | 8.1 NOTE | Operational planning takes information security and data protection into account | Information security and data protection | New in IA9100 | Evidenced | IA-8.1-01: Conforming (Programme plan PP-3101 data protection section).
11 | 0.1, 0.2 | The introduction now treats organizational culture and ethical behavior as part of an effective quality management system | Organizational culture and ethics | New in IA9100 | Partly evidenced | Your AS9100D self-assessment answer QB-5.1-005 is an Observation (See audit programme for 5.1). IA-5.1.1-01: Conforming (Quality culture objective QO-2026-04). IA-5.1.1-02: Conforming (Code of conduct HR-POL-07). |  | State in the quality manual how culture and ethical behavior support the quality management system, and point to the policy and objectives that carry it. | 21
12 | 5.1.1 k | Top management sets goals and objectives that build a quality culture, consistent with policy, vision, values and context | Organizational culture and ethics | New in IA9100 | Evidenced | IA-5.1.1-01: Conforming (Quality culture objective QO-2026-04).
13 | 5.1.1 l | Top management promotes an ethical work environment: conduct policy, training, reporting channels, investigation and resolution, and no penalty for raising a concern | Organizational culture and ethics | New in IA9100 | Gap | IA-5.1.1-03: Nonconforming (Ethics covered at hire only; no refresher). IA-5.1.1-05: Nonconforming (No record of concerns raised or how they were resolved). IA-5.1.1-04: Observation (Not confidential and not advertised for safety concerns). Your AS9100D self-assessment answer QB-5.1-005 is an Observation (See audit programme for 5.1). IA-5.1.1-02: Conforming (Code of conduct HR-POL-07). |  | Issue a code of conduct, train people on it periodically, provide a confidential channel for concerns (product-safety concerns included), and record how each concern was investigated and resolved without penalty to the person who raised it. | 8
14 | 7.1.4 NOTE | Culture (quality, ethical behavior, product and personnel safety, quality of work life) is named as a factor of the work environment | Organizational culture and ethics | New in IA9100 | Evidenced | IA-5.1.1-01: Conforming (Quality culture objective QO-2026-04).
15 | 7.3 | People are aware of the importance of ethical behavior | Organizational culture and ethics | Unchanged text, now part of a wider requirement | Gap | IA-5.1.1-03: Nonconforming (Ethics covered at hire only; no refresher). |  | Record ethics awareness training for everyone, and repeat it at a set interval. | 13
16 | 8.4.3 | External providers are told of the importance of ethical behavior | Organizational culture and ethics | Unchanged text, now part of a wider requirement | Partly evidenced | IA-8.4.3-01: Observation (Covers conformity and safety; ethics not mentioned). |  | Add the importance of ethical behavior to your purchase order terms or supplier quality manual, and record it in the flow-down register. | 27
17 | 7.1.5.1 NOTE | Measurement variation is understood through measurement systems analysis, gauge R&R or attribute studies | Product quality planning and foreign object prevention | New in IA9100 | Partly evidenced | Open findings in your records: Capability claim resting on an unqualified gauge (SPC-3107-HARD, SPC-3101-BORE, SPC-3101-FLANGE); Measurement system not acceptable (GRR-HT2205). 3 records in your MSA studies (GRR-BG6601, GRR-CMM4401, GRR-HT2205). | SPC-3107-HARD, SPC-3101-BORE, SPC-3101-FLANGE, GRR-HT2205, GRR-BG6601, GRR-CMM4401 | Run and record measurement systems analysis for the gauges that measure key characteristics, and act on studies that are not acceptable. Start with SPC-3107-HARD, SPC-3101-BORE, SPC-3101-FLANGE, GRR-HT2205, GRR-BG6601, GRR-CMM4401. | 16
18 | 8.1 b NOTE | Statistical techniques support process control: key characteristics, capability, control plans, statistical process control | Product quality planning and foreign object prevention | Strengthened | Partly evidenced | Open findings in your records: High-priority failure mode with no control (FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02 and 16 more); Process not capable of its tolerance (SPC-3107-HARD). 5 records in your control plans (CP-MER-3101, CP-MER-3103, CP-MER-3104, CP-MER-3105 and 1 more). 5 records in your capability studies (SPC-3101-BORE, SPC-3104-BORE, SPC-3101-FLANGE, SPC-3108-HINGE and 1 more). | FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106, SPC-3107-HARD, CP-MER-3101, CP-MER-3103, CP-MER-3104, CP-MER-3105, CP-MER-3106, SPC-3101-BORE, SPC-3104-BORE, SPC-3101-FLANGE, SPC-3108-HINGE | Keep control plans and capability studies for key characteristics current, and act on processes whose capability is low. Start with FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03 and 25 more. | 23
19 | 8.1 k | Operations are planned to prevent, detect and mitigate foreign objects and debris | Product quality planning and foreign object prevention | Strengthened | Partly evidenced | Your AS9100D self-assessment answer QB-8.5.1-011 is an Observation (See audit programme for 8.5.1). Your AS9100D self-assessment answer QB-5.1-004 is an Observation (See audit programme for 5.1). Your PFMEAs and control plans (PFMEA-MER-3101, PFMEA-MER-3102, PFMEA-MER-3103, PFMEA-MER-3104 and 7 more) name no foreign-object failure mode or control, while your records hold foreign-object events (NCR-MER-213, CAPA-MER-013). Foreign-object training is recorded for 3 people; for 1 it is not current (MER-E020). IA-8.1-02: Conforming (FOD procedure QP-8.5-09; area audits). Your foreign object and debris document is controlled and current (DOC-MER-039). | PFMEA-MER-3101, PFMEA-MER-3102, PFMEA-MER-3103, PFMEA-MER-3104, NCR-MER-213, CAPA-MER-013, MER-E020, DOC-MER-039 | Make foreign object and debris a planned control: name it in PFMEAs and control plans where it can occur, keep the FOD procedure current and train the people in FOD areas. Start with PFMEA-MER-3101, PFMEA-MER-3102, PFMEA-MER-3103, PFMEA-MER-3104, NCR-MER-213, CAPA-MER-013 and 2 more. | 25
20 | 8.1 NOTE | Product and service provision is planned as integrated, phased processes (project or program management, APQP) | Product quality planning and foreign object prevention | Strengthened | Partly evidenced | IA-8.1-03: Observation (Single checklist; no phased gate reviews). Your AS9100D self-assessment answer QB-8.1.1-003 is an Observation (See audit programme for 8.1.1). Open findings in your records: Part submission warrant unsigned (PPAP-MER-3101, PPAP-MER-3102, PPAP-MER-3103, PPAP-MER-3104, PPAP-MER-3105 and 1 more); High-priority failure mode with no control (FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02 and 16 more). | PPAP-MER-3101, PPAP-MER-3102, PPAP-MER-3103, PPAP-MER-3104, PPAP-MER-3105, PPAP-MER-3106, FM-3101-03, FM-3101-07, PFMEA-MER-3101, FM-3102-01, FM-3102-02, FM-3102-03, FM-3102-04, FM-3102-07, PFMEA-MER-3102, FM-3103-03, FM-3103-07, PFMEA-MER-3103, FM-3104-03, FM-3104-07, PFMEA-MER-3104, FM-3105-03, FM-3105-07, PFMEA-MER-3105, FM-3106-03, FM-3106-07, PFMEA-MER-3106 | Plan each new product or program in phases with gate reviews (APQP or equivalent), and close each phase's outputs (PFMEA, control plan, PPAP) before the next. Start with PPAP-MER-3101, PPAP-MER-3102, PPAP-MER-3103, PPAP-MER-3104, PPAP-MER-3105, PPAP-MER-3106 and 21 more. | 24
21 | 8.3.2.1 | Where appropriate, design and development is divided into distinct activities with their tasks, resources, responsibilities, inputs and outputs | Product quality planning and foreign object prevention | Strengthened | Evidenced | IA-8.3.2.1-01: not applicable (Build to print; no design responsibility).
22 | 8.1.4 a | People in procurement, receiving inspection, shipping inspection and material control are trained to recognize and prevent counterfeit parts | Counterfeit parts prevention | Was guidance; now a requirement | Gap | Your AS9100D self-assessment answer QB-8.1.4-002 is Nonconforming (See audit programme for 8.1.4): the base this change builds on is not in place. 11 of the 11 people listed in receiving inspection have no current counterfeit-part training (MER-E008, MER-E014, MER-E019, MER-E023, MER-E028, MER-E037, MER-E038, MER-E043 and 3 more). IA-8.1.4-01: Conforming (Counterfeit awareness training records CT-2026). | MER-E008, MER-E014, MER-E019, MER-E023, MER-E028, MER-E037, MER-E038, MER-E043, MER-E046, MER-E065, MER-E067 | Train everyone in procurement, receiving inspection, shipping inspection and material control in counterfeit-part awareness and prevention, and record it in the training matrix. Start with MER-E008, MER-E014, MER-E019, MER-E023, MER-E028, MER-E037 and 5 more. | 2
23 | 8.1.4 b | A parts obsolescence monitoring program is applied | Counterfeit parts prevention | Was guidance; now a requirement | Gap | IA-8.1.4-02: Nonconforming (No obsolescence monitoring of purchased parts). Your AS9100D self-assessment answer QB-8.1.4-003 is Nonconforming (See audit programme for 8.1.4): the base this change builds on is not in place. |  | Set up parts obsolescence monitoring for the parts you buy, so that end-of-life parts are found before you are pushed to unapproved sources. | 9
24 | 8.1.4 c | Parts are bought from original or authorized manufacturers, authorized distributors or other approved sources | Counterfeit parts prevention | Was guidance; now a requirement | Gap | Your AS9100D self-assessment answer QB-8.1.4-001 is Nonconforming (See audit programme for 8.1.4): the base this change builds on is not in place. Your AS9100D self-assessment answer QB-8.1.4-002 is Nonconforming (See audit programme for 8.1.4): the base this change builds on is not in place. 2 counterfeit cases trace to a broker or a source not on your approved list (CF-MER-001, CF-MER-002). Open findings in your records: Supplier on probation still delivering (SUP-MER-01, SUP-MER-02, SUP-MER-03, SUP-MER-12, SUP-MER-17). IA-8.1.4-03: Conforming (Approved supplier list ASL-2026 source column). | CF-MER-001, CF-MER-002, SUP-MER-01, SUP-MER-02, SUP-MER-03, SUP-MER-12, SUP-MER-17 | Buy only from original manufacturers, their authorized distributors or sources you have approved, and record the source's authorization on the supplier list. Start with CF-MER-001, CF-MER-002, SUP-MER-01, SUP-MER-02, SUP-MER-03, SUP-MER-12 and 1 more. | 3
25 | 8.1.4 d | Parts and components can be traced to their original or authorized manufacturer | Counterfeit parts prevention | Was guidance; now a requirement | Partly evidenced | 11 of 40 lots in your traceability register have no conforming certificate (TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15, TRC-MER-19, TRC-MER-22, TRC-MER-25 and 3 more). Open findings in your records: Lot held at receiving for its certificate of conformity (TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15 and 6 more). | TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15, TRC-MER-19, TRC-MER-22, TRC-MER-25, TRC-MER-35, TRC-MER-36, TRC-MER-38 | Hold a conforming certificate that traces each lot to its original or authorized manufacturer before the lot is released. Start with TRC-MER-01, TRC-MER-02, TRC-MER-03, TRC-MER-05, TRC-MER-15, TRC-MER-19 and 5 more. | 15
26 | 8.1.4 e | Verification and test methods are used to detect counterfeit parts | Counterfeit parts prevention | Was guidance; now a requirement | Gap | Your AS9100D self-assessment answer QB-8.1.4-002 is Nonconforming (See audit programme for 8.1.4): the base this change builds on is not in place. IA-8.1.4-04: Conforming (Receiving inspection plan RI-04). |  | Define the receiving checks and tests used to detect counterfeit parts, by part risk, and record them on each receipt. | 10
27 | 8.1.4 f | Counterfeit-part reports from external sources (for example GIDEP) are monitored | Counterfeit parts prevention | Was guidance; now a requirement | Partly evidenced | IA-8.1.4-05: Observation (Alerts received; no record of checking them against stock). |  | Assign someone to review external counterfeit-part reports (for example GIDEP alerts) at a set interval and record what was checked against your parts. | 22
28 | 8.1.4 g | Suspect or detected counterfeit parts are segregated, contained and reported | Counterfeit parts prevention | Was guidance; now a requirement | Partly evidenced | Open findings in your records: Counterfeit part case open (CF-MER-001, CF-MER-002, CF-MER-003). Every counterfeit case is segregated, and those past investigation are reported (CF-MER-001, CF-MER-002, CF-MER-003). | CF-MER-001, CF-MER-002, CF-MER-003 | Quarantine every suspect part, contain where it went, and report each confirmed or suspect case externally (for example to GIDEP and the customer). Start with CF-MER-001, CF-MER-002, CF-MER-003. | 18
29 | 8.4.1 | External providers are required to apply suitable controls to their own direct and sub-tier providers | Sub-tier supplier control | Unchanged text, now part of a wider requirement | Partly evidenced | Your flow-down register records 7 requirements flowed to suppliers (FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17); none requires a supplier to flow them down to its own sub-tier suppliers. Open findings in your records: Customer requirement not flowed down (FLD-MER-01, FLD-MER-02, FLD-MER-03, FLD-MER-04, FLD-MER-05 and 4 more); Customer requirement only partly flowed down (FLD-MER-09, FLD-MER-10, FLD-MER-16, FLD-MER-18). IA-8.4.1-01: Conforming (Supplier quality manual SQM rev F section 4). | FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17, FLD-MER-02, FLD-MER-03, FLD-MER-04, FLD-MER-05, FLD-MER-12, FLD-MER-09, FLD-MER-10, FLD-MER-18 | Require each supplier, in the purchase order or supplier quality manual, to control its own suppliers to your requirements, and record that requirement in the flow-down register. Start with FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16 and 9 more. | 26
30 | 8.4.3 k.d | The level of control of direct and sub-tier external providers is determined and communicated | Sub-tier supplier control | New in IA9100 | Gap | IA-8.4.3-02: Nonconforming (Level of control not decided per supplier). Your flow-down register records 7 requirements flowed to suppliers (FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17); none requires a supplier to flow them down to its own sub-tier suppliers. | FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16, FLD-MER-17 | Decide the level of control for each direct supplier and its sub-tier suppliers, and state it in the information you send them. Start with FLD-MER-01, FLD-MER-06, FLD-MER-11, FLD-MER-13, FLD-MER-15, FLD-MER-16 and 1 more. | 4
31 | 8.5.1.3 | Production process verification goes beyond first article inspection, covering new or changed processes | Production process verification | Strengthened | Gap | Your AS9100D self-assessment answer QB-AS9102-001 is Nonconforming (See audit programme for 8.5.1): the base this change builds on is not in place. IA-8.5.1.3-01: Observation (First part only; process changes not verified). Open findings in your records: First article report not signed (FAI-MER-101, FAI-MER-102, FAI-MER-103, FAI-MER-106, FAI-MER-107 and 10 more); Accepted first article report with no signatures on record (FAI-MER-104, FAI-MER-105, FAI-MER-109). | FAI-MER-101, FAI-MER-102, FAI-MER-103, FAI-MER-106, FAI-MER-107, FAI-MER-108, FAI-MER-110, FAI-MER-111, FAI-MER-112, FAI-MER-113, FAI-MER-114, FAI-MER-115, FAI-MER-116, FAI-MER-117, FAI-MER-118, FAI-MER-104, FAI-MER-105, FAI-MER-109 | Verify every new or changed production process (not only the first part) before production, and record the result with the first article report. Start with FAI-MER-101, FAI-MER-102, FAI-MER-103, FAI-MER-106, FAI-MER-107, FAI-MER-108 and 12 more. | 11

## About
SAMPLE REPORT. Sample report. Contains no export-controlled (ITAR/EAR) data.
IA9100 Transition Gap Analysis
Measured against the IA9100 changes the IAQG has published to date (draft); the final text may still change them.
Prepared for Meridian Aerostructures. Contains proprietary methodology of Aegis Technologies Inc.; licensed for the recipient's internal use only. Not to be reproduced, shared outside the recipient's organization, used to train or prompt AI systems, or used to develop competing products.
Prepared for | Meridian Aerostructures
Site | -
Report date | 2026-10-22
Basis | IAQG IA9100 key-change summaries (Nov 2023); draft
Templates read | 01_KPI_Scorecard.csv, 02_CAPA.csv, 03_Risk_Register.csv, 04_Suppliers.csv, 05_FAI_First_Article_Inspection.csv, 06_MRB_Material_Review_Board.csv, 07_Training_Matrix.csv, 08_Calibration.csv, 09_Special_Processes.csv, 10_Action_Register.csv, 11_Configuration_BOM.csv, 12_Documents.csv, 13_Audit_Findings.csv, 14_Traceability.csv, 15_Flowdown.csv, 16_Recovery_Timeline.csv, 17_Nonconformances.csv, 18_Calibration_Results.csv, 19_Supplier_Receipts.csv, 20_Supplier_Quality_Events.csv, 21_Supplier_Audits.csv, 22_PFMEA.csv, 23_Control_Plan.csv, 24_PPAP.csv, 25_SPC_Measurements.csv, 26_MSA_Gage_RR.csv, 27_Internal_Audit_Programme.csv, 28_Change_Requests.csv, 29_KPI_Trend_Weekly.csv, 30_Clause_Self_Assessment.csv, 31_Counterfeit_Cases.csv, 32_RACI.csv
Data completeness | Complete. Every register supplied for this report was read in full; no section is blank because records could not be read.
Clause numbers | A change's clause number is the one the published summaries give; where they give none, the AS9100D clause is used and marked.
Organizational culture and ethics | The published draft wording on culture and ethics may still change in the final text.